## Sheet1
Gantt Chart for Bugdroid Project
| Week of |  |  | Feb. 1 | [6 empty] | Feb. 8 | [6 empty] | Feb. 15 | [6 empty] | Feb. 22 | [6 empty] | Feb. 29 | [6 empty] | Mar. 7
ID | Task Name | Predecessors | Expected TAT | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
1 | Identify Project/Start | N/A | 0
2 | Create 3-D model | N/A | 1 Day
3 | Create 2-D slice files | 3 | 1 Day
4 | Have pieces cut | 4 | 4 Days
5 | Take pictures throughout | N/A | N/A
6 | Update Webpage | 3 | 1 Day
7 | Assemble Pieces | 4 | 2 Days
8 | Update Webpage | 7 | 1 Day
9 | Cover pieces | 7 | 1 Day
10 | Finalize Project | 9 | 1 Day
11 | Update Webpage | 10 | 1 Day
| Buffer Time | N/A | [36 empty] | DUE
Guide
Task Finished
To be accomplished